## Cover Sheet
Environmental Desk Based Assessment - Section 1
Project Name: | WR076 SWN_RIVER BOLLIN | Author | [✂] (UU Environmental Planner, PLE)
Date: | 23/05/2022 | Reviewer | [✂] (UU Head of PLE)
Project Summary:
Local Authority(ies) | Trafford Council
Planning permission | Yes
Environmental Impact Assessment (EIA) | Screening Required - High Risk
Abstraction Licence | Yes
Risk Rating (1 low, 2 medium, 3 high) |  | Summary/Recommendations
Risk Rating | 3 | An Enviornmental Impact Assessment (EIA) is likely to be required to support the Planning Application, due to the nature and scale of development within an area of Greenbelt, landscape protection areas, wildlife corridors and and on the edge of a rural village. This will add significant time and cost onto the programme. A detailed site selection exercise and early consultation with the Local Planning Authority will be required before the exact location can be determined. The HS2 Safeguarding Zone is impacted by the pipeline route and WTW siting. Consultation with the LPA and HS2 will be required. Located within Flood Risk Zone 2 and 3. Engagement regarding the siting and design required with the EA. A flood risk assessment would be required to accompany the planning application. Potential need to relocate from the flood zone. The scheme potentially should be considered in conjunction with WR076. It is unlikely Planning Permission will be approved for two WTWs in close proximity​ although the fact they are in separate local authority areas would help
1
2
3
Note on A13: 3 (HIGH) = Significant PLE constraints with long lead in time, which have potential to conflict with project output date, eg highly sensitive scheme, with complex consenting requirements and extensive stakeholder engagement, advance surveys or consents required and/or advanced site preparation required within outside of specific season.Significant likelihood of conflict with environmental, third party and/or customer constraints. Applicable agreements, permissions or regulatory consents will be extremely challenging to obtain. To enable successful delivery of the project there will be a need for multiple/complex activities including stakeholder/public engagement, consent applications, land access/acquisition, surveys and mitigation. There is significant potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals. 2 (MEDIUM) = Significant PLE constraints which can be managed within the proposed project output date. Lead in times still required for ecology, landscape and planning requirements. Applicable agreements, permissions or regulatory consents may be challenging to obtain. To enable successful delivery of the project there will be a need for activities which may include stakeholder/public engagement, consent applications, land access/acquisition, surveys and mitigation. There is potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals. 1 (LOW) = PLE issues identified but which can be managed through specialist resource and BAU processes within proposed output date. Some limited potential for conflict with environmental, third party and/or customer constraints. Applicable agreements, permissions or regulatory consents are likely to be necessary but straightforward. There is low potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals.

## Identify
Constraints Checklist - Section 2
Ref | Category | Affected/ Required? Yes/No/Potentially | Details | Reference
1 | Designations | Yes | Planning Policy Designations: The proposed [✂] location and the majority of the pipeline route are within areas of designated Greenbelt, Areas of Landscape Protection and Wildlife Corridors. Visual Impact will be a prime concern. The HS2 safeguarding zone is impacted by the proposed pipeline route. Stautory Designated Sites: None. | Refer to Constraints tab and Environmental Review Plan
3 | Trees & Hedgerows | Yes | Trees and hedgerows are located within and in close proximity to the proposed [✂] location and pipeline route. There will be a need for a tree survey and an assessment of effects/impacts including proposed retention, protection and mitigation of effects on trees.
4 | Amenity Landscapes (e.g. Sports Pitches, Greenspace, Green-infrastructure) | Potentially | Impacts to amenity spaces should be avoided where possible.
5 | Access land - Village Green, Common Land, Millennium Greens etc. | No
6 | Heritage and Archaeology | Yes | An archaelogical desk based assessment will be required with possible further investigations and mitigation measures.
| Tree Preservation Order | Potentially | Further consultation with Trafford Council is required to determine the location of any TPO trees. TPO trees should be avoided where possible.
7 | Public Right of Way | Yes | The pipeline route is located along the Trans Pennine Trail Cycle path. This should be kept open for the duration of the construction works and may have to be avoided all together Further consultation with Trafford Council is required to determine the location of other Rights of Way in the area.
8 | Main Rivers | Yes | The River Bollin is a designated main river. A Flood Risk Activity Permit will be required from the Environment Agency for any works within 8m unless exempt. A Flood Risk Assessment and Geomorphological Assessment will be required to support the applications. Early consultation with the Environment Agency will be required.
9 | Ordinary Watercourses | Yes | The pipeline route crosses ordinary watercourses. Any works which impact on these and where existing crossing points or no dig techniques can't be used will need approval from the Lead Local Flood Authority.
| Flood Risk Zone | Potentially | The proposed WTW and some of the pipeline route are located within Flood Risk Zone 2 and 3. Engagement regarding the siting and design required with the EA. A flood risk assessment would be required to accompany the planning application. Potential need to relocate from the flood zone.
16 | EIA Screening Opinion | Yes | The development proposals exceeds the thresholds set out in Schedule 2 of the Town and Country Planning (Environmental Impact Assessment) Regulations 2017 and as such an EIA Screening Opinion will need to be submitted to Trafford Council. The scheme potentially should also be considered in conjuntion with WR105a.
17 | Environmental Impact Assessment | Potentially | It is likely that an Environmental Impact Assessment will be required to support the Planning Application. This will add significant time and cost onto the programme.
18 | Planning Permission | Yes | Planning Permission will be required for all above ground development required in connection with the construction of the new [✂] and abstraction infrastructure. Permitted development rights will in effect be removed if the development requires EIA.
29 | Discharge Permit | Yes | Any new discharge would require a permit from the Environment Agency.
30 | Abstraction Licence | Yes | Any new abstraction will require an Abstraction Licence which should be confirmed with and obtained from the Environment Agency.
Yes
No
Potentially
Note on A2: Rimmer, Tom: • If any aspect is affected/potentially affected set this out in this section and provide brief details of the constraint/requirement and any reference for future Information for Tenderers (IfT). • If unaffected click “no” and this aspect will not appear in the next tab…

## Timeline
Third Party, Environment and Customer Action Plan - Section 3 - Timeline
The specific timeline for the Project will be developed in collabrative planning sessions. The typical windows and timescales for key Third Party and PLE Activities are summarised below
PLEASE NOTE TIMESCALES BELOW ARE BASED ON TYPICAL TIMESCALES AND STATUATORY DETERMINATION PERIODS AND THE TIMESCALES FOR APPROVAL ON PROJECTS COULD BE SIGNIFICANTLY LONGER AND SHOULD BE SET OUT IN COLLABRATIVE PLANNING SESSIONS
Application Type | Restrictions | External Cost | Timescale (Weeks)
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Abstraction | If Pre App Required assume 8 months required for this | Yes | Timescale (Weeks) 1: Currently 6 months till scheme allocated to a case officer - this is subject to change | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE
Impoundment | If Pre App Required assume 8 months required for this | Yes | Timescale (Weeks) 1: Currently 6 months till scheme allocated to a case officer - this is subject to change | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE
EIA Screening (LPA) |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
EIA Screening (Marine) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Marine Licence |  | Yes | [52 empty] | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 20
Footpath Diversions (Temp) |  | Yes | Timescale (Weeks) 1: Between 6 and 14 weeks depending on the council
Footpath Diversions (Perm) |  | Yes
Tree Works (TPO or Conservation Area) |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Hedgerow Removal Notice |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Planning (Water) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Planning (Waste) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 15
Planning (EIA) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 18
Planning (Condition Discharge) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Scheduled Monument Consent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Listed Building Consent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Reg 76 / 77 Application |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 3
EA Flood Risk Activity Permit |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Lead Local Flood Authority Consent |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 8
S278 | Can only be applied for once Planning Permission Granted | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 14
S184 | Can only be applied for once Planning Permission Granted | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 9
Habitat Regulations Assessment |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
SSSI Assent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Protected Species Licence | Can only be applied for once Planning Permission Granted | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Industrial Emmisions Permit |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Hazardous Substances Consent | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Approximate period for application to be allocated to case officer
Typical duration for registration of application once allocated to case officer
Statuatory determination period

## Constraints
Proposed WTW Location | Pipeline route area
EA Flood Risk Map - proposed WTW location | Tree Preservation Order Check
TBC - requires consultation with LPA
Public Rights of Way | Local Plan - Proposed WTW location
[✂]
TBC - requires consultation with LPA
[✂]
Trans Pennine Trail Cycle Path
[✂]

## Environmental Review Plan
[✂]