## Cover Sheet
Environmental Desk Based Assessment - Section 1
Project Name: | WR049d SWN_RIVER RIBBLE | Author | [✂] (UU Environmental Planner, PLE)
Date: | 10/05/2022 | Reviewer | [✂] (UU Head of PLE)
Project Summary:
Local Authority(ies) | South Ribble Chorley
Planning permission | Yes
Environmental Impact Assessment (EIA) | High Risk
Abstraction Licence | Yes
Risk Rating (1 low, 2 medium, 3 high) |  | Summary/Recommendations
Risk Rating | 3 | Due to the length of the pipeline route it is highly likely an EIA will be required. This will add significant time and cost onto the programme. In this event all permitted development rights are withdrawn and planning permission will be required for the overall scheme [✂]. A new abstraction licence will be require which has a lead time of approximately 2 years. Early consultation will be required with the relevent stakeholders to determine the exact location of the abstraction point. Early external consultation will be required with third parties including land owners, South Ribble and Chorley LPAs, local communities and interest groups before the exact routeing of the pipeline is confirmed
1
2
3
Note on A13: 3 (HIGH) = Significant PLE constraints with long lead in time, which have potential to conflict with project output date, eg highly sensitive scheme, with complex consenting requirements and extensive stakeholder engagement, advance surveys or consents required and/or advanced site preparation required within outside of specific season.Significant likelihood of conflict with environmental, third party and/or customer constraints. Applicable agreements, permissions or regulatory consents will be extremely challenging to obtain. To enable successful delivery of the project there will be a need for multiple/complex activities including stakeholder/public engagement, consent applications, land access/acquisition, surveys and mitigation. There is significant potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals. 2 (MEDIUM) = Significant PLE constraints which can be managed within the proposed project output date. Lead in times still required for ecology, landscape and planning requirements. Applicable agreements, permissions or regulatory consents may be challenging to obtain. To enable successful delivery of the project there will be a need for activities which may include stakeholder/public engagement, consent applications, land access/acquisition, surveys and mitigation. There is potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals. 1 (LOW) = PLE issues identified but which can be managed through specialist resource and BAU processes within proposed output date. Some limited potential for conflict with environmental, third party and/or customer constraints. Applicable agreements, permissions or regulatory consents are likely to be necessary but straightforward. There is low potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals.

## Identify
Constraints Checklist - Section 2
Ref | Category | Affected/ Required? Yes/No/Potentially | Details | Reference
1 | Designations | Yes | Planning Policy Designations: The majority of the pipeline route and Rivington [✂] is located within an area of designated Greenbelt. Visual impact will be a prime concern. Stautory Designated Sites: None. Ancient Woodland: The current pipeline route impacts an area of ancient woodland near Salmesbury.This should be avoided. Local Level Wildlife Sites: There are some local level wildlife sites impacted by the current pipeline route. It is recommended to avoid these where possible. | Refer to Constraints tab and Environmental Review Plan
2 | Trees & Hedgerows | Yes | Due to the length and route of the pipeline there will be impacts to trees and hedgerows. See above for information on Salmesbury ancient woodland. There will be a need for a tree survey and an assessment of effects/impacts including proposed retention, protection and mitigation of effects on trees.
3 | Amenity Landscapes (e.g. Sports Pitches, Greenspace, Green-infrastructure) | Potentially | Impacts to amenity spaces should be avoided where possible.
4 | Access land - Village Green, Common Land, Millennium Greens etc. | Potentially | Impacts to access land should be avoided where possible
5 | Heritage and Archaeology | Yes | An archaelogical desk based assessment will be required with possible further investigations and mitigation measures.
6 | Tree Preservation Order | Potentially | There are TPO trees within the vicinity of the pipeline route. These should be avoided where possible.
7 | Public Right of Way | Yes | The pipeline route will impact Public Rights of Way. PRoW closures will be required if these are to be diverted or closed during the construction phase.
8 | Main Rivers | Yes | The River Ribble and River Darwen would be impacted by construction activies in relation to the new abstraction point and pipeline route. A Flood Risk Activity Permit will be required from the Environment Agency for any works within 8m unless exempt. A Flood Risk Assessment and Geomorphological Assessment will be required to support the applications. Early consultation with the Environment Agency and Natural England will be required.
9 | Ordinary Watercourses | Yes | The pipeline route crosses several ordinary watercourses. Any works which impact on these and where existing crossing points or no dig techniques can't be used will need approval from the Lead Local Flood Authority.
10 | Flood Risk Zone | Yes | Several areas of the pipeline route and abstraction point are within Flood Risk Zones 2 and 3. Any works outside of Flood Zone 1 a will require a Flood Risk Assessment to accompany the Planning Application.
11 | EIA Screening Opinion | Potentially | The development proposals exceeds the thresholds set out in Schedule 2 of the Town and Country Planning (Environmental Impact Assessment) Regulations 2017 and as such an EIA Screening Opinion would need to be submitted to Chorley and South Ribble Local Planning Authorities.
12 | Environmental Impact Assessment | Yes | Due to the location and nature of the development it is likely that an Environmental Impact Assessment would be required to support the Planning Application. This will add significant time and cost onto the programme.
13 | Planning Permission | Yes | In the event that an EIA is required all Permitted Development Rights would be withdrawn and Planning Permission would be required for the overall scheme. Otherwise planning permission would be needed for any new buildings at the [✂]
14 | Discharge Permit | Yes | Any new discharge would require a permit from the Environment Agency.
15 | Abstraction Licence | Yes | The new abstraction would require an Abstraction Licence from the Environment Agency.
Yes
No
Potentially
Note on A2: Rimmer, Tom: • If any aspect is affected/potentially affected set this out in this section and provide brief details of the constraint/requirement and any reference for future Information for Tenderers (IfT). • If unaffected click “no” and this aspect will not appear in the next tab…

## Timeline
Third Party, Environment and Customer Action Plan - Section 3 - Timeline
The specific timeline for the Project will be developed in collabrative planning sessions. The typical windows and timescales for key Third Party and PLE Activities are summarised below
PLEASE NOTE TIMESCALES BELOW ARE BASED ON TYPICAL TIMESCALES AND STATUATORY DETERMINATION PERIODS AND THE TIMESCALES FOR APPROVAL ON PROJECTS COULD BE SIGNIFICANTLY LONGER AND SHOULD BE SET OUT IN COLLABRATIVE PLANNING SESSIONS
Application Type | Restrictions | External Cost | Timescale (Weeks)
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Abstraction | If Pre App Required assume 8 months required for this | Yes | Timescale (Weeks) 1: Currently 6 months till scheme allocated to a case officer - this is subject to change | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE
Impoundment | If Pre App Required assume 8 months required for this | Yes | Timescale (Weeks) 1: Currently 6 months till scheme allocated to a case officer - this is subject to change | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE
EIA Screening (LPA) |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
EIA Screening (Marine) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Marine Licence |  | Yes | [52 empty] | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 20
Footpath Diversions (Temp) |  | Yes | Timescale (Weeks) 1: Between 6 and 14 weeks depending on the council
Footpath Diversions (Perm) |  | Yes
Tree Works (TPO or Conservation Area) |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Hedgerow Removal Notice |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Planning (Water) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Planning (Waste) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 15
Planning (EIA) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 18
Planning (Condition Discharge) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Scheduled Monument Consent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Listed Building Consent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Reg 76 / 77 Application |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 3
EA Flood Risk Activity Permit |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Lead Local Flood Authority Consent |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 8
S278 | Can only be applied for once Planning Permission Granted | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 14
S184 | Can only be applied for once Planning Permission Granted | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 9
Habitat Regulations Assessment |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
SSSI Assent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Protected Species Licence | Can only be applied for once Planning Permission Granted | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Industrial Emmisions Permit |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Hazardous Substances Consent | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Approximate period for application to be allocated to case officer
Typical duration for registration of application once allocated to case officer
Statuatory determination period

## Environmental Review Plan
[✂]

## Rivington Constraints
Rivington WTW | Local Plan
EA Flood Risk Map | TPO Check
[✂] | [✂]
PROW Check
[✂]