## Cover Sheet
Environmental Desk Based Assessment - Section 1
Project Name: | WR105a GWE_LYMM a1 | Author | [✂] (UU Environmental Planner, PLE)
Date: | 10/05/2022 | Reviewer | [✂] (UU Head of PLE)
Project Summary:
Local Authority(ies) | Warrington Borough Council
Planning Permission | Yes
Environmental Impact Assessment (EIA) | Potentially - High Risk
Abstraction Licence | Existing Abstraction - increase abstraction within LicQ
Risk Rating (1 low, 2 medium, 3 high) |  | Summary/Recommendations
Risk Rating | 3 | An Enviornmental Impact Assessment (EIA) is likely to be required to support the Planning Application, due to the nature and scale of development within an area of Greenbelt and open countryside and on the edge of a rural village. This will add significant time and cost onto the programme. A detailed site selection exercise and early consultation with the Local Planning Authority will be required before the exact location can be determined. A strategy to demolish and make good [✂] at Lymm is likely to be required due to it's location within a conservation area. The scheme potentially should be considered in conjunction with WR076. It is unlikely Planning Permission will be approved for two [✂] in close proximity​.
1
2
3

## Identify
Constraints Checklist - Section 2
Ref | Category | Affected/ Required? Yes/No/Potentially | Details | Reference
1 | Designations | Yes | Planning Policy Designations: The proposed [✂] location is located within an area of designated Greenbelt and an area of Strategic Green Links. Visual impact will be a prime concern. [✂] Lymm is within a Conservation Area. Stautory Designated Sites: None. | Refer to Constraints tab and Environmental Review Plan
2 | Trees & Hedgerows | Yes | There are trees and hedgerows within the vicinity of the proposed [✂]. There will be a need for a tree survey and an assessment of effects/impacts including proposed retention, protection and mitigation of effects on trees.
3 | Amenity Landscapes (e.g. Sports Pitches, Greenspace, Green-infrastructure) | Yes | The [✂] is an area of open greenspace, adjacent to community allotments.
4 | Access land - Village Green, Common Land, Millennium Greens etc. | No
5 | Heritage and Archaeology | Yes | An archaelogical desk based assessment will be required with possible further investigations and mitigation measures.
6 | Tree Preservation Order | Yes | Trees within the Conservation Area are protected by a TPO.
7 | Public Right of Way | Yes | The Trans Pennine Trail is located to the south of the proposed [✂] location. This should be kept open for the duration of the construction works.
8 | Main Rivers | Yes | Sow Brook and the tributory that runs adjacent to the proposed [✂] location are designated main river. A Flood Risk Activity Permit will be required from the Environment Agency for any works within 8m unless exempt. A Flood Risk Assessment and Geomorphological Assessment will be required to support the applications. Early consultation with the Environment Agency will be required.
9 | Ordinary Watercourses | Yes | An ordinary watercourse runs adjacent to the working area. Any works which impact on these such as realignment, and where existing crossing points or no dig techniques can't be used will need approval from the Lead Local Flood Authority.
10 | Flood Risk Zone | Yes | Part the [✂] location is within flood risk zone 2. Any works outside of Flood Zone 1 a will require a Flood Risk Assessment to accompany the Planning Application.
11 | EIA Screening Opinion | Yes | An EIA Screening Opinion will be required to be submitted to Warrington Borough Council as the development involves the construction [✂].
12 | Environmental Impact Assessment | Yes | It is likely that an Environmental Impact Assessment will be required to support the Planning Application. This will add significant time and cost onto the programme.
13 | Planning Permission | Yes | Planning Permission will be required for all above ground development required in connection with the construction of a new [✂] on third party land. Permitted development rights will in effect be removed if the development requires EIA.
14 | Discharge Permit | Yes | Any new discharges will require a permit from the EA
15 | Abstraction Licence | Potentially | Any amendments to the exisiting abstraction may require a permit from the EA
Yes
No
Potentially

## Timeline
Third Party, Environment and Customer Action Plan - Section 3 - Timeline
The specific timeline for the Project will be developed in collabrative planning sessions. The typical windows and timescales for key Third Party and PLE Activities are summarised below
PLEASE NOTE TIMESCALES BELOW ARE BASED ON TYPICAL TIMESCALES AND STATUATORY DETERMINATION PERIODS AND THE TIMESCALES FOR APPROVAL ON PROJECTS COULD BE SIGNIFICANTLY LONGER AND SHOULD BE SET OUT IN COLLABRATIVE PLANNING SESSIONS
Application Type | Restrictions | External Cost | Timescale (Weeks)
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Abstraction | If Pre App Required assume 8 months required for this | Yes | Timescale (Weeks) 1: Currently 6 months till scheme allocated to a case officer - this is subject to change | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE
Impoundment | If Pre App Required assume 8 months required for this | Yes | Timescale (Weeks) 1: Currently 6 months till scheme allocated to a case officer - this is subject to change | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE
EIA Screening (LPA) |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
EIA Screening (Marine) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Marine Licence |  | Yes | [52 empty] | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 20
Footpath Diversions (Temp) |  | Yes | Timescale (Weeks) 1: Between 6 and 14 weeks depending on the council
Footpath Diversions (Perm) |  | Yes
Tree Works (TPO or Conservation Area) |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Hedgerow Removal Notice |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Planning (Water) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Planning (Waste) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 15
Planning (EIA) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 18
Planning (Condition Discharge) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Scheduled Monument Consent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Listed Building Consent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Reg 76 / 77 Application |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 3
EA Flood Risk Activity Permit |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Lead Local Flood Authority Consent |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 8
S278 | Can only be applied for once Planning Permission Granted | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 14
S184 | Can only be applied for once Planning Permission Granted | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 9
Habitat Regulations Assessment |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
SSSI Assent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Protected Species Licence | Can only be applied for once Planning Permission Granted | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Industrial Emmisions Permit |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Hazardous Substances Consent | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Approximate period for application to be allocated to case officer
Typical duration for registration of application once allocated to case officer
Statuatory determination period

## Constraints
Proposed WTW location | Local Plan
[✂] | [✂]
EA Flood Risk Map | Tree Preservation Order Check
[✂] | [✂]
Public Rights of Way |  | Conservation Area
[✂] |  | [✂]